## actions
id | owner | deadline | what it is (read-only)
act-2026-recovery | Angelo Nahavitatsara / MadAvance | 2027-01-31 | Run the 2026 calendar recovery round across the whole portfolio — not a sample.
act-742896839 | Lanja, mWater group administrator |  | 742896839 is in mWater but not in the MadAvance group — resolved as to cause.
act-adopt-consolidated-gardien-calendar | Jan | 2026-10-31 | Adopt the consolidated gardien calendar SOP.
act-calendar-custody | Angelo Nahavitatsara / MadAvance | 2026-09-26 | Standing rule, to be issued to every field team today: NO CALENDAR MAY BE REPLACED UNTIL THE PREVIOUS ONE HAS BEEN PHOTO
act-calendar-v13 | Adriaan Mol | 2026-10-10 | Print and distribute calendar template v1.4, withdrawing year-printed stock as v1.4 reaches each district.
act-call-service-visit | Angelo Nahavitatsara / MadAvance | 2026-10-31 | Retrain the call team on the routine-service-visit option.
act-carbon-year-basis | James Walker |  | Supply the per-year carbon activity basis, or withdraw the per-year table.
act-close-eight-2-2 | MadAvance | 2026-11-30 | Close the eight 2.2.1(d) records.
act-close-out-6-5 | Adriaan |  | Close out the unexplained residual against the January population run.
act-close-s4-16-car-2 | James Walker, with Angelo | 2026-11-30 | Correct the SDWS 3 evidence record, and commission the parallel validation round.
act-complete-accuracy-assessment-calendar | Adriaan Mol | 2026-10-31 | Complete the accuracy assessment of the calendar extraction.
act-confirm-india-mark-capacity | MadAvance field teams |  | Confirm the India Mark capacity cap.
act-confirm-maroantsetra-fnrb-value | James Walker | 2026-10-31 | Confirm the Maroantsetra fNRB value at %.
act-confirm-whether-ersdws-v2 | James Walker | 2026-09-30 | Confirm whether ERSDWS v2.0 applies to this VPA before renewal.
act-dashboard-gap | Lanja Randriamanantena / MadAvance | 2026-10-17 | Reconcile the gap between the MadAvance dashboard and our register.
act-decide-how-treat-67 | James Walker, with Jan | 2026-10-31 | Decide how to treat the points with no usable calendar image: exclude, or estimate.
act-decommission-inactivity-field | — | 2026-09-21 | Decided 21 September 2026: SaniTap will not decommission or retire water points for inactivity.
act-define-maintenance-record-becomes | Adriaan |  | Define how a maintenance record becomes a days-out-of-service count.
act-design-change-q1-2027 | James Walker, data by Adriaan |  | Design change with the Q1 2027 verification: apply v2.0 to 2025, and correct the VPA-DD.
act-down-no-repair | Angelo Nahavitatsara / MadAvance | 2026-10-17 | Close the call-centre down reports that have no repair record.
act-duplicate-codes-sweep | Adriaan Mol | 2026-09-21 | Clear the six duplicated question codes on the other three forms.
act-emergency-event-form | Angelo Nahavitatsara / MadAvance | 2026-10-31 | Settle where SDWS 3 emergency-event evidence is actually recorded — the form the SOP names does not exist.
act-enduro-feed | Jan de Graaf | 2026-10-31 | Endur’O onboarding: a dispensing-events feed from Curtech — device id, timestamp, litres, card and credits for every dis
act-enduro-move-register-fully | Jan, with Coddy | 2026-10-31 | Endur’O onboarding into mWater: move the register fully into mWater, in seven steps.
act-enduro-onboard-1-enumerators | Coddy | 2026-10-03 | Endur’O onboarding: populate the enumerator team so the two registration forms open in the field app.
act-enduro-onboard-2-register-sites | Coddy with Jan | 2026-10-31 | Endur’O onboarding: register every managed Endur’O site with the System and Distribution Point forms.
act-enduro-onboard-3-bind-taps | Coddy | 2026-10-31 | Endur’O onboarding: bind every smart tap to its water point by the paired-timestamp test dispense.
act-enduro-onboard-5-calibration | Ralf van Veenendaal (Curtech) | 2026-10-31 | Endur’O onboarding: a calibration certificate for every installed meter, traceable to its device id (Gold Standard SDWS
act-enduro-onboard-6-kiosk-wq | Jan de Graaf with Cathy Andriambololonirina (Mandie) | 2026-10-16 | Endur’O onboarding: a water-quality test at the dispensing point of the managed kiosk, bound to the water point, not the
act-enduro-onboard-7-piped-sdws27 | Coddy with Jan | 2026-10-31 | Endur’O onboarding: piped maintenance, repair and days-not-operational records in mWater — the SDWS 27 evidence.
act-enduro-people-source | Adriaan Mol |  | Record where the Endur'O people figure comes from.
act-enduro-refresh | Adriaan Mol |  | Re-confirm the hand-entered Endur'O figures.
act-establish-renewal-dates-current | James Walker | 2026-10-31 | Establish renewal dates and current status for the four baseline parameters.
act-establish-renewal-dates-four | James Walker |  | Establish renewal dates for the four baseline parameters.
act-figure-residue | Adriaan Mol |  | Resolve the remaining unsourced figures.
act-find-source-annual-independent | Adriaan |  | Find a source for the annual independent cross-check of people per premises.
act-fleet-growth | Jan de Graaf | 2026-10-17 | The carbon fleet has not grown in nine months. Establish what the pipeline actually is.
act-form-consolidation | Adriaan Mol |  | Decide whether to consolidate the Marolinta borehole form into the works form.
act-freeze-estate-map-when | Adriaan |  | Freeze the estate map when an edition is archived.
act-gaps-doc | Jan de Graaf | 2026-10-03 | Correct the carbon-data-gaps source document: it says the cookstove overlap has not been calculated, and it has.
act-gs-validation-withdrawal-watch | James Walker | 2026-12-31 | Watch for Gold Standard’s correction of the v2.0 quarterly Option 3 validation.
act-identify-count-institutional-premises | MadAvance |  | Identify and count institutional premises inside the service areas.
act-indiamark-premises | James Walker | 2026-10-31 | Settle the India Mark premises figure — or .
act-make-calendar-photograph-mandatory | Lanja | 2026-10-31 | Make the calendar photograph a mandatory field on both visit forms.
act-mar-admin-fields | Angelo Nahavitatsara / MadAvance |  | Set the administrative fields and pump model on the Marolinta records in mWater.
act-mar-functional-status | Adriaan Mol |  | Fill “Statut fonctionnel actuel” on the new-construction records.
act-mar-missing-boreholes | Angelo Nahavitatsara / MadAvance |  | Enter the Marolinta new-borehole records that are missing.
act-mar-missing-rehabs | Angelo Nahavitatsara / MadAvance |  | Record the rehabilitations that have no record at all.
act-mar-new-construction-gap | Angelo Nahavitatsara / MadAvance |  | Record the new boreholes that have no record at all.
act-mar-technical-values | Angelo Nahavitatsara / MadAvance |  | Check the repeated technical values with the drilling supervisor.
act-mar-water-quality | Lanja Randriamanantena / MadAvance |  | Get a passed E. coli test at the point of collection on every Marolinta borehole.
act-mar-which-form | Adriaan Mol |  | Get the field teams onto the current first-rehabilitation form.
act-marolita-spelling | Angelo Nahavitatsara |  | Correct the village spelling on the works-form records that spell it Marolita.
act-mor-1b-betanatanana-go-look | Jan / Endur’O team |  | 1b. Betanatanana — go and look at this well
act-mor-bring-back-site-lists | Jan / Endur’O team |  | 10. Bring back site lists with coordinates for Andaingo and Fieferana / Manjakandriana
act-mor-correct-two-sampling-records | Jan / Endur’O team |  | 8. Correct two sampling records
act-mor-count-draw-off-point | Jan / Endur’O team |  | 3. Count every draw-off point on the system
act-mor-fill-three-new-fields | Jan / Endur’O team |  | 9. Fill the three new fields on the results form from the next round
act-mor-fix-type-sampled-point | Jan / Endur’O team |  | 4. Fix the type of each sampled point, once
act-mor-have-those-five-records | Jan / Endur’O team |  | 2. Have those five records shared with SaniTap
act-mor-households-people-served-per | Jan / Endur’O team |  | 5. Households and people served per draw-off point
act-mor-re-take-gps-fix | Jan / Endur’O team |  | 1. Re-take the GPS fix at Amboasary Gara
act-mor-record-what-community-drank | Jan / Endur’O team |  | 6. Record what each community drank before the system
act-mor-remove-reclassify-two-test | Jan / Endur’O team |  | 7. Remove or reclassify two test records in the hand-pump register
act-mor-submit-drafts | Jan / Endur’O team |  | Submit the draft new-construction records on the Moramanga deployment.
act-moramanga-post-rehab-wq | Jan de Graaf with Endur’O |  | Post-rehabilitation water-quality tests on the four Moramanga piped systems; record the sampled tap on every result.
act-move-stroke-test-sop | Jan | 2026-10-31 | Approve stroke-test SOP v2.1 in French and English, move the French version into the SOPs folder, and retire v2.0.
act-move-weekly-mwater-backup | Adriaan |  | Move the weekly mWater backup off the laptop.
act-mwater-approval-policy | Angelo Nahavitatsara / MadAvance with Jan de Graaf | 2026-10-31 | Define what approving an mWater record means, then apply it only where it buys something.
act-mwater-backup-restore-check | Adriaan Mol | 2026-10-02 | Check what the mWater backup restore brought back, and that nothing edited after it was lost.
act-mwater-mg-locale | Lanja Randriamanantena / MadAvance | 2026-10-03 | Add the Malagasy locale to the Entretien préventif form, so Malagasy labels stop having to lead the French string.
act-mwater-year-required | Adriaan Mol | 2027-01-31 | Make mWater question 2.15.7 required, once v1.4 stock and the SOP are in the field in both districts.
act-no-works-record | Angelo Nahavitatsara / MadAvance |  | Enter a works record, or remove from the register, for every point that has neither.
act-per-diem | Adriaan Mol | 2026-10-31 | Redesign the per-diem system so it pays for pumps completed, not days in the field.
act-photo-conditional-on-presence | Adriaan Mol | 2026-09-21 | Make the calendar photograph conditional on a calendar being present on the repair-after-breakdown form, as it now is on
act-photo-misfiled | Adriaan Mol | 2026-10-31 | Move the misfiled photographs to the question they belong on.
act-piped-fnrb | James Walker |  | Settle the fNRB for the piped VPA before its VPA-DD is submitted.
act-piped-usage-survey | James Walker |  | Annual usage survey for the piped systems — separate from the hand-pump survey; JMP core questions, household size, usag
act-piped-wq-misfiled-742895333 | Lanja Randriamanantena / MadAvance | 2026-10-10 | Two water-quality results for hand pump 742895333 (Sainte Luce) were filed on the piped results form 0ac68d82; re-enter
act-point-use-round-one | MadAvance / Cathy |  | Point-of-use round one.
act-population-rerun | Adriaan Mol |  | Re-run the population model whenever the portfolio grows.
act-printed-year-meaning | Angelo Nahavitatsara / MadAvance | 2026-10-17 | Establish what the year printed on a gardien calendar is meant to denote, and whether sheets are issued with a forward y
act-produce-s4-19-cl | Adriaan, submitted by James Walker | 2026-10-31 | Produce the installation database.
act-put-current-methodology-vpa | James Walker | 2026-09-30 | Put the current methodology and our VPA-DD into the Central Data Hub.
act-put-usage-question-live | Adriaan / MadAvance |  | Put the usage question on a live mWater form and run usage survey round one.
act-re-run-improved-cookstove | Angelo, tracked by Jan |  | Re-run the improved-cookstove usage question every year.
act-reconcile-cookstove-water-programmes | James Walker on method, Adriaan on data |  | Reconcile the cookstove and water programmes for double counting.
act-recreate-gardien-calendar-controlled | Jan | 2026-10-31 | Recreate the gardien calendar as a controlled document.
act-reduced-performance | Angelo Nahavitatsara / MadAvance |  | Check the pumps reported with reduced performance that are still counted as working.
act-refresh-extract | Adriaan Mol |  | Refresh the mWater extract before each edition.
act-rehab-recording | Angelo Nahavitatsara / MadAvance | 2026-10-03 | Reconcile the Marolinta count: the minutes say 10 and 10, the form holds and .
act-reissue-calendars-new-blank | Jan with Angelo | 2026-12-31 | Reissue calendars on the new blank template, on visits already scheduled.
act-repair-double-entry | Lanja Randriamanantena |  | Decide what to do with one repair recorded twice across the form migration.
act-repair-time | Jan de Graaf | 2026-12-31 | Call-centre response and report-back time — an operational performance target, explicitly not a carbon figure.
act-repeat-breakdown | Jan de Graaf |  | Decide whether the two repeat-breakdown pumps need a second water point rather than a fifteenth repair.
act-resolve-sdws-27-sdws | James Walker | 2026-10-15 | Resolve the SDWS 27 / SDWS 28 numbering, and the calibration requirement.
act-resolve-water-point-type | Jan | 2026-10-31 | Resolve the water point type contradiction on 987623517.
act-restore-preventive-maintenance-visit | Jan | 2026-11-30 | Restore the preventive-maintenance visit rate (SDWS 27).
act-retrain-field-teams-how | Angelo | 2026-10-31 | Retrain field teams on how to photograph the calendar.
act-route-plans | Jan de Graaf | 2026-10-17 | Build a catch-up route plan for Marolinta, and keep Fort-Dauphin’s current.
act-run-sdws-26-premises | Angelo, tracked by Jan | 2026-10-31 | Run the SDWS 26 premises-served survey, and report the precision actually achieved.
act-run-stroke-test-sdws | Angelo, tracked by Jan | 2026-12-15 | Run the stroke test on the SDWS 23 sample, to the SOP.
act-sdws26-annual-round | Angelo Nahavitatsara, MadAvance water team |  | Run the SDWS 26 usage round every year, and fix the cluster shortfall.
act-sdws26-approve-2025 | MadAvance |  | Approve the November 2025 usage responses in mWater.
act-sdws26-instrument-review | James Walker |  | Review and sign off the SDWS 26 usage instrument before the field round.
act-sdws27-basis | James Walker | 2026-10-03 | Settle the SDWS 27 basis with Gold Standard.
act-sdws3-operating-status | Adriaan Mol | 2026-10-17 | Add an operating-status question to the SDWS 3 water-quality forms.
act-sensor-cost-benefit | Adriaan Mol | 2026-10-31 | Cost-benefit of a sensor on every pump against the sample of 100.
act-sensor-definition | James Walker | 2026-10-10 | Put the sensor definition to Gold Standard.
act-sensor-sample | Adriaan Mol | 2026-10-03 | Brief Ralf van Veenendaal at Curtech on the fleet-wide unit count and the calibration sample — they are two different nu
act-settle-baseline-boiling-device | James Walker on method, Adriaan on data | 2026-11-30 | Settle the baseline boiling device for stove-holding households in Anosy.
act-sop-calendar-v17-signoff | Angelo Nahavitatsara / MadAvance | 2026-10-10 | Approve calendar SOP v1.7, brief every field team on it in French, then retire v1.6.
act-standardised-stroke-test-basis | MadAvance |  | Standardised stroke test — the basis is settled.
act-transcription-round | MadAvance — transcriber to be named | 2026-10-10 | Run the transcription validation round.
act-type3-cap | James Walker |  | Decide the route before the point count reaches the small-scale Type 3 annual cap.
act-undatable | Angelo Nahavitatsara / MadAvance | 2026-10-17 | Quantify the water points behind the undatable sheets, and merge with the reissue list.
act-update-parameters-workbook-cite | James Walker | 2026-10-31 | Update the parameters workbook to cite the applied basis.
act-update-sops-portfolio-figures | Jan | 2026-10-31 | Update the SOP’s portfolio figures.
act-v2-adherence | James Walker |  | Methodology version adherence — standing item.
act-v2-confidence-intervals | James Walker | 2026-10-17 | Retain confidence intervals, not just point estimates, on every sampled parameter from now on.
act-v2-embodied | James Walker | 2026-10-31 | Start recording commissioning year and technology category as a monitoring output.
act-v2-nonclaiming | James Walker | 2026-10-17 | Close the individual-level consent gap — the community-level notice is already in place.
act-v2-sample-size | James Walker | 2026-10-10 | Re-scope every sample against the v2.0 minimum of .
act-v2-stove-stacking | James Walker | 2026-10-31 | Add a stove-stacking question to the annual monitoring survey.
act-v2-stroke-test | James Walker | 2026-10-10 | Reconcile the stroke-test SOP with v2.0, which recognises it and adds a condition.
act-verification-fnrb-correction | James Walker |  | Include the Maroantsetra fNRB correction in the Q1 2027 verification submission.
act-visit-collapse | Jan de Graaf | 2026-09-30 | Maintenance visit frequency has collapsed, and calendar coverage depends on it directly.
act-visit-three-marolinta-points | Angelo, tracked by Jan | 2026-12-31 | Visit the three Marolinta points that have no photograph of any kind.
act-wq-retest | Lanja Randriamanantena / MadAvance |  | Confirm the one failed E. coli test was retested.

## read me
SaniTap weekly water report - owner and deadline
One row per action in the report. Edit column B (owner) and column C
(deadline) only. The build reads this file each Monday and renders
those two fields from it.
Column A is the action id and must not be changed: it is how a row is
matched to the report. Column D is a copy of the title, for reading
only - editing it changes nothing.
Status, the counts, and whether an item is open or closed are NOT in
this workbook and cannot be set here. They are computed from stored
closing conditions every build, so an item closes when the data says
it is done and reopens if that stops being true.
If the build cannot read this file, the report falls back to the
owners and deadlines written in the page and says so on the page.
Seeded 2026-09-28 from 129 actions by tools/make_owner_workbook.py